## Sheet1
MERKATO DEVELOPMENT TIMELINE
Phase | Timeline | Key Features | Definition of Done
Phase 1 — Foundations | 2–3 weeks | User roles: Customer, Vendor, Admin DB schema includes delivery_time fields Basic dashboards Deployment to Vercel/Render/Supabase Health checks + CI/CD setup | Users can log in by role, dashboards visible, DB persists users
Phase 2 — Catalog & Product Management | 2–3 weeks | Vendor KYC/approval by Admin Vendor dashboard for product CRUD Customer catalog: categories, filters, product pages Delivery Time Setter: vendor sets per-product delivery estimates Admin sets global delivery defaults | Admin approves vendor → Vendor uploads product → Customers see with delivery time estimate
Phase 3 — Cart & Checkout | 2–3 weeks | Cart with multi-vendor support Checkout flow: shipping address, payment gateway Vendor-managed shipping option (flat rate, delivery estimates) Customer chooses delivery option at checkout Admin can override vendor delivery time | Customer adds item to cart → Completes checkout with delivery estimate visible → Vendor receives order
Phase 4 — Orders & Fulfillment | 2–4 weeks | Vendors accept/reject orders Shipping label generation via carrier APIs Real-time tracking integration Customer order tracking & return requests Vendor/admin manual override of status Delivery KPIs tracking (speed, return rate) | Vendor accepts order → Generates label → Customer can track → Return requests possible
Phase 5 — Payments & Finance | 2–3 weeks | Commission system (e.g., 5%) Vendor payouts via Stripe Connect or regional gateways Invoices/receipts auto-generated Refund & dispute management Shipping costs integrated into payouts and commissions | Customer pays → Platform cut calculated → Vendor payout visible → Invoice generated
Phase 6 — Admin Ops & Logistics Hubs | 2–4 weeks | Regional hub support: inventory, bulk consolidation, returns Admin logistics dashboard (carrier performance, hub turnover, SLA compliance) Vendor performance metrics (on-time %, returns) Global delivery time overrides Peak season contingency planning | Admin can manage hubs, vendors see performance metrics, SLA monitoring active, customers receive hub-optimized deliveries